## Runbook Rehost
Runbook and Sequence
Read before you start: 1. Please go through the description section below. If any questions, contact the Migration Team. 2. All white cells are mandatory, except "Comment" column (which is optional). 3. To add the entire row(s) anywhere in each table (as long as before the 'END' row), follow instructions below: − Go to the row header/ number at the left hand side and copy the row you'd like to replicate; − Go to the row header where you'd like to insert row(s), right Click and select "Insert copied cells" − Tidy up the formula in the row below the new row(s) inserted, and renumber the row sequence. 3. Steps that are not required should be marked accordingly in Column G.. 4. For numbered cells, you will need to re-number them.
Sub ID | Task List | Accountability | Due Date | Time Estimate | GEN2KTBRK01 | GEN2KTDMZ01 | GEN2KTHM01 | GEN2KTINT01 | GEN2KTINT02 | GEN2KTRDS01 | GEN2KTRDS02 | GEN2KTRDS03 | GEN2KTSQL01 | Comments
1000 | Migration planning activities |  |  |  | ]
All preparation activities required to enable the change to be properly defined, scheduled, and documented before implementation (e.g., stakeholder meetings, resource bookings, communications).
1001 | Scheduling confirmed with Customer and Account Manager | Sapphire Project Manager |  |  | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started
1002 | Passport & Runbook signed off | Sapphire Programme Team |  |  | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started
1003 | Change Request raised and approved | Sapphire Project Manager |  |  | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | Replication Agent installation and cutover window has to adapt
1004 | Application Test Plan Provided and approved | Sapphire App Team |  |  | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started
END
2000 | Pre-Implementation Tasks (Build and Configure)
Technical steps happen right before Implementation starts. These are tasks that are not part of the Implementation window and must have no risk. Include activities such as access checks, open bridge call, back-up data, etc.
2001 | Disable server from patch-management OS schedules from on-premises | Sapphire Infrastructure Team |  |  | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started
2002 | Citrix Cloud Controller to be installed and configured on-prem | Sapphire Infrastructure Team |  |  | Not Required | Not Required | Not Required | Not Required | Not Required | Not Required | Not Required | Not Required | Not Required | Must be done before the replication agent can be installed. If this step is required in previous customer migration tbc
2003 | Install AWS MGN & SSM - and reboot to verify all services come up properly | Sapphire Infrastructure Team |  |  | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | Reboot is required to ensure there are no services that are not configured to correctly start at boot that are required. We can proceed without and check during a test deploy if we can't do this in a Production environment HOWEVER it may impact delivery time if we cannot validate at an earlier stage.
2004 | Create local Cloudreach_user | Sapphire Infrastructure Team |  |  | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started
2005 | Verify that Servers are healthy. | Sapphire Infrastructure Team |  |  | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started
2006 | Ensure Replication job kicked off replication in the migration tooling dashboard | Cloudreach Migration Team |  |  | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started
2007 | Check required Service Quota | Cloudreach Migration Team |  |  | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started
2008 | ABOVE STEPS SHOULD BE COMPLETED BEFORE PRE-IMPLEMENTATION CALL AND FURTHER STEPS
2009 | Configure MGN server launch settings (disable Instance type right sizing) | Cloudreach Migration Team |  |  | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started
2010 | Configure MGN EC2 Launch Template (only change Instance Type, Subnet & Security groups) | Cloudreach Migration Team |  |  | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started
2011 | On healthy replication, deploy MGN Launch Template via Test mode and validate using isolated Security Groups. Complete boot test. | Cloudreach Migration Team |  |  | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started
2012 | Prepare Terraform code required for the customer and make sure the map-migrated tag is applied to all eligable resources | Cloudreach Migration Team |  |  | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started
2013 | Test deployment using the Terraform code using mock AMIs. Import the servers created in the test phase and cleanup. | Cloudreach Migration Team |  |  | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started
2014 | Update the Launch Template after test launch |  |  |  | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started
2015 | Complete Infrastructure-Side Testing | Cloudreach Migration Team |  |  | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started
2016 | Confirm Pre-Implementation Actions complete | Cloudreach Project Manager |  |  | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started
2017 | Send final comms to Customer and respective teams | Sapphire Programme Team |  |  | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started
END
3000 | Testing & Go-Live Readiness
All necessary testing needs to be completed successfully before the cutover starts. This is not considered part of the Change window (e.g., Unit, System, Regression, Integration, User Acceptance, Operational Acceptance Testing). Where a change is being performed in a non-production environment as pre-implementation testing for a subsequent production environment implementation. Testing should be attached or location referenced in the change.
3001 | Confirm MGN replication is fully synced | Cloudreach Migration Team |  |  | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started
3002 | Go/No Go Decision - for Cutover | Sapphire Programme Team |  |  | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | Ensure all resources from all parties required are on the call
3003 | Disable VMs from on-prem backup schedule | Sapphire Infrastructure Team |  |  | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started
3004 | Suspend all monitoring on on-premises servers | Sapphire Infrastructure Team |  |  | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started
END
4000 | Cutover steps
Include all implementation activities within the change window, including post-implementation testing, verification to assess need to remediate, checkpoint/decision making meetings to agree whether to remediate (where appropriate), communications, and status updates etc. Any activities that may cause an OUTAGE or performance degradation should be included in the Implementation section. Must be documented at a low level with step-by-step detail such that it can be printed out and followed to carry out the implementation. reference to other documentation during the implementation is only permitted if they are clearly referenced here. Detail in the comments field if the referenced materials are attached to the RFC or provide the URL/file location where the documents can be accessed.
4001 | Graceful shutdown of the application service (if applicable) | Sapphire App Team |  |  | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started
4002 | (Database) Graceful shutdown of the database service (if applicable) | Sapphire App Team |  |  | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started
4003 | Shutdown On-premises Database Servers | Sapphire Infrastructure Team |  |  | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | Re-hosted machines share the same hostname so we must shut down the original before bringing up the new one. Use command "shutdown -s" to avoid any Windows updates to run during shutdown.
4004 | Shutdown On-premises Servers (Application and others) | Sapphire Infrastructure Team |  |  | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | Re-hosted machines share the same hostname so we must shut down the original before bringing up the new one. Use command "shutdown -s" to avoid any Windows updates to run during shutdown.
4005 | Validate that on-premises Application Servers are shutdown | Sapphire Infrastructure Team |  |  | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started
4006 | Initiate MGN Failover and validate failover instance | Cloudreach Migration Team |  |  | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started
4007 | Remove applicable legacy agents/tools: On-prem tool agents | Cloudreach Migration Team |  |  | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | Could include but not limited VMware tools, backup agents Local user or respective user access for Cloudreach is required e.g. "Cloudreach_user"
4008 | Create AMI from MGN Failover instance | Cloudreach Migration Team |  |  | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started
4009 | Import resources in the Terraform stack | Cloudreach Migration Team |  |  | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started
4010 | Finalise MGN Failover by deploying AMI with IaC | Cloudreach Migration Team |  |  | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started
4011 | Implement & Update DNS records | Sapphire Infrastructure Team |  |  | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started
4012 | Write down final instances IPs into the Infrastructure Manifest tab | Cloudreach Migration Team |  |  | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started
4013 | Run a full update on the AWS drivers and Agents and restart the servers | Cloudreach Migration Team |  |  | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started
4014 | Test & validate required network connectivity & security elements (SGs, Routes, L7 Domain) | Cloudreach Migration Team |  |  | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started
4014 | Infrastructure-Side Testing & Finalize Cutover in MGN | Cloudreach Migration Team |  |  | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started
4015 | Validate Sapphire connectivity and testing (if required) | Sapphire Infrastructure Team |  |  | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started
4016 | Sapphire to request and provide a new HANA license | Sapphire App Team |  |  | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started
4017 | Start application services | Sapphire App Team |  |  | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started
4018 | Client-Side Application Testing | Sapphire App Team |  |  | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | 3rd Party and/or customer could be involved
4019 | Change Complete | Sapphire App Team |  |  | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started
4020 | Rollback Decision | Sapphire Programme Team |  |  | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started
4021 | Uninstall MGN and remove local cloudreach_user (if not automatically done) | Cloudreach Migration Team |  |  | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started
4022 | Validate tagging | Cloudreach Migration Team |  |  | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | Guarantee the map-migrated-tag is included
END
5000 | Rollback activities (where required)
Include all activities required to remediate the change should the implementation tests indicate issues. If there are several remediation plan decision points, clearly document the possible start points and associated steps. All remediation testing, checkpoints, status updates, decision making are to be included. The Worst Case Scenario (based on the last possible remediation point) remediation window, including testing time, must be incorporated as part of the change window. If assessment indicated that remediation is either not possible or will not be undertaken due to Business requirements, this must be clearly articulated with full justification provided. Reference to attached documents is acceptable.
5001 | Stop / Deallocate provisioned AWS resources | Cloudreach Migration Team |  |  | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started
5002 | Roll back DNS Changes | Sapphire Infrastructure Team |  |  | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started
5003 | Bring on-premises resources back | Sapphire Infrastructure Team |  |  | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started
5004 | Restart application services | Sapphire App Team |  |  | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started
5005 | Post-Rollback Application Testing | Sapphire App Team |  |  | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started
5006 | Client-Side Application Testing | Sapphire App Team |  |  | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | 3rd Party and/or customer could be involved
END
6000 | Post Implementation activities
Activities to complete the Change that are outside the change window.
6001 | Initiate 5-day hypercare period | Cloudreach Migration Team |  |  | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started
6002 | Notify stakeholders of successful cutover (IT service desk & others) | Sapphire Programme Team |  |  | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started
6003 | Update Handover Documentation | Cloudreach Migration Team |  |  | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started
6004 | Handover to Ops Support | Cloudreach Migration Team |  |  | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | Includes handover of relevant credentials, SSH keys, database passwords etc
END
7000 | Operations Onboarding
A list of activities for Operations to complete in regards to the support required for the application.
7001 | Handover Passport to Ops | Cloudreach Migration Team |  |  | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started
7002 | Validate resources against Application Passport | Sapphire Operations Team |  |  | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started
7003 | Check access to instance(s) | Sapphire Operations Team |  |  | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started
7004 | Raise onboarding issue to Sapphire Programme Team | Sapphire Operations Team |  |  | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started
7005 | Install required tools | Sapphire Operations Team |  |  | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started
7006 | Validate Backup Compliance | Sapphire Operations Team |  |  | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started
7007 | Internal Sign Off | Sapphire Operations Team |  |  | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started
7008 | Customer Sign Off - Go Live | Sapphire Programme Team |  |  | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started
7009 | Send comms to all stakeholders | Sapphire Programme Team |  |  | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started
END
8000 | Decommissioning
A list of activities to complete in regards to decomissioning the on-premises application infrastructure.
8001 | Raise request for decommissioning | Sapphire Programme Team |  |  | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started | Not Started
END

## Runbook Re-Platform
Runbook and Sequence
Read before you start: 1. Please go through the description section below. If any questions, contact the Migration Team. 2. All white cells are mandatory, except "Comment" column (which is optional). 3. To add the entire row(s) anywhere in each table (as long as before the 'END' row), follow instructions below: − Go to the row header/ number at the left hand side and copy the row you'd like to replicate; − Go to the row header where you'd like to insert row(s), right Click and select "Insert copied cells" − Tidy up the formula in the row below the new row(s) inserted, and renumber the row sequence. 3. Steps that are not required should be marked accordingly in Column G.. 4. For numbered cells, you will need to re-number them.
ID | Task List | Accountability | Due Date | Time Estimate | DKIR01DCP01 | DKIR01DCP02 | DKIR01HANAP01 | Comments
1000 | Migration planning activities
All preparation activities required to enable the change to be properly defined, scheduled, and documented before implementation (e.g., stakeholder meetings, resource bookings, communications).
1001 | Scheduling confirmed with Customer and Account Manager | Sapphire Project Manager |  |  | Not Started | Not Started | Not Started
1002 | Passport & Runbook signed off | Sapphire Programme Team |  |  | Not Started | Not Started | Not Started
1003 | Change Request raised and approved | Sapphire Project Manager |  |  | Not Started | Not Started | Not Started
1004 | Application Test Plan Provided and approved | Sapphire App Team |  |  | Not Required | Not Required | Not Required
END
2000 | Pre-Implementation Tasks (Build and Configure)
Technical steps happen right before Implementation starts. These are tasks that are not part of the Implementation window and must have no risk. Include activities such as access checks, open bridge call, back-up data, etc.
2001 | Prepare Terraform code required for the customer | Cloudreach Migration Team |  |  | In Progress | Not Started | Not Started
2002 | Test deployment using the Terraform code using mock AMIs. Import the servers created in the test phase and cleanup. | Cloudreach Migration Team |  |  | Not Started | Not Started | Not Started
2003 | Provision new infrastructure for Re-Platform resources | Cloudreach Migration Team |  |  | Not Started | Not Started | Not Started
2004 | If Linux servers provisioned, create users and groups present in the Infra manifest with the given UID/GID | Cloudreach Migration Team |  |  | Not Required | Not Required | Not Required
2005 | Install and configure Cloudwatch and SSM | Cloudreach Migration Team |  |  | Not Started | Not Started | Not Started
2006 | Validate Sapphire connectivity and testing (if required) | Sapphire Infrastructure Team |  |  | Not Started | Not Started | Not Started
2007 | Install ManageEngine, CrowdStrike and any Infrastructure Services required | Sapphire Infrastructure Team |  |  | Not Started | Not Started | Not Started | Possible solution: Sapphire provides the installation packages to include them in the roll out
2008 | (Application/Domain Controller) Install and Configure application on new cloud infrastructure | Sapphire App Team |  |  | Not Started | Not Started | Not Started
2009 | (Database) Configure DB components on the provisioned infrastructure | Sapphire Infrastructure Team |  |  | Not Started | Not Started | Not Started
2010 | (Database) Export On-Prem DB & Import to new setup | Sapphire Infrastructure Team |  |  | Not Started | Not Started | Not Started
2011 | Confirm necessary public and private DNS changes | Cloudreach Migration Team |  |  | Not Started | Not Started | Not Started | Assumes Sapphire owns public and private DNS configuration
2012 | Test & validate required network connectivity & security elements (SGs, Routes, L7 Domain) | Cloudreach Migration Team |  |  | Not Started | Not Started | Not Started | If outbound proxy URLs are present in the passport, those needs to be added to the AWS Network Firewall Outbound. Update on spreadsheet as well as code.
2013 | Complete Infrastructure-Side Testing | Cloudreach Migration Team |  |  | Not Started | Not Started | Not Started
2014 | Write down final instances IPs into the Infrastructure Manifest tab | Cloudreach Migration Team |  |  | Not Started | Not Started | Not Started
2015 | Client-Side Application Testing | Sapphire App Team |  |  | Not Started | Not Started | Not Started | 3rd Party and/or customer could be involved Domain Controller can be promoted at this stage
2016 | Validate Tagging | Cloudreach Migration Team |  |  | Not Started | Not Started | Not Started | Guarantee the AWS map-migrated-tag is included
2017 | Validate Shared Service changes | Cloudreach Migration Team |  |  | Not Required | Not Required | Not Started
2018 | Validate 3party and API connectivity | 3rd Party |  |  | Not Required | Not Required | Not Started
2019 | Update Security Groups based on validation and testing | Cloudreach Migration Team |  |  | Not Started | Not Started | Not Started
2020 | Confirm Pre-Implementation Actions complete | Cloudreach Project Manager |  |  | Not Started | Not Started | Not Started
2021 | Send final comms to Customer and respective teams | Sapphire Programme Team |  |  | Not Started | Not Started | Not Started
END
3000 | Testing & Go-Live Readiness
All necessary testing needs to be completed successfully before the cutover starts. This is not considered part of the Change window (e.g., Unit, System, Regression, Integration, User Acceptance, Operational Acceptance Testing). Where a change is being performed in a non-production environment as pre-implementation testing for a subsequent production environment implementation. Testing should be attached or location referenced in the change.
3001 | (Database) Perform final sync of Database | Sapphire App Team |  |  | Not Started | Not Started | Not Started
3005 | Go/No Go Decision - for Cutover | Sapphire Programme Team |  |  | Not Started | Not Started | Not Started
3002 | Disable VMs from on-prem backup schedule | Sapphire Infrastructure Team |  |  | Not Started | Not Started | Not Started
3003 | Suspend all monitoring on on-premises servers | Sapphire Infrastructure Team |  |  | Not Started | Not Started | Not Started
END
4000 | Cutover steps
Include all implementation activities within the change window, including post-implementation testing, verification to assess need to remediate, checkpoint/decision making meetings to agree whether to remediate (where appropriate), communications, and status updates etc. Any activities that may cause an OUTAGE or performance degradation should be included in the Implementation section. Must be documented at a low level with step-by-step detail such that it can be printed out and followed to carry out the implementation. reference to other documentation during the implementation is only permitted if they are clearly referenced here. Detail in the comments field if the referenced materials are attached to the RFC or provide the URL/file location where the documents can be accessed.
4001 | (Application and others) Graceful shutdown of the application service (if applicable) | Sapphire App Team |  |  | Not Started | Not Started | Not Started
4002 | (Database) Graceful shutdown of the database service (if applicable) | Sapphire App Team |  |  | Not Started | Not Started | Not Started
4003 | (Database) Shutdown On-premises Database Servers | Sapphire Infrastructure Team |  |  | Not Started | Not Started | Not Started
4004 | (Application and others) Shutdown On-premises Servers | Sapphire Infrastructure Team |  |  | Not Started | Not Started | Not Started | Re-hosted machines share the same hostname so we must shut down the original before bringing up the new one.
4005 | Validate that on-premises Servers are shutdown | Sapphire Programme Team |  |  | Not Started | Not Started | Not Started
4006 | Update DNS records | Sapphire Infrastructure Team |  |  | Not Started | Not Started | Not Started
4007 | Validate rehost server part of the application are done and ready to connect to the re-platform server | Cloudreach Migration Team |  |  | Not Started | Not Started | Not Started
4008 | Validate 3rd Party connectivity (if required) | Sapphire App Team |  |  | Not Started | Not Started | Not Started
4009 | Client-Side Application Testing | Sapphire App Team |  |  | Not Started | Not Started | Not Started | 3rd Party and/or customer could be involved
4010 | Change Complete | Sapphire App Team |  |  | Not Started | Not Started | Not Started
4011 | Rollback Decision | Sapphire Programme Team |  |  | Not Started | Not Started | Not Started
END
5000 | Rollback activities (where required)
Include all activities required to remediate the change should the implementation tests indicate issues. If there are several remediation plan decision points, clearly document the possible start points and associated steps. All remediation testing, checkpoints, status updates, decision making are to be included. The Worst Case Scenario (based on the last possible remediation point) remediation window, including testing time, must be incorporated as part of the change window. If assessment indicated that remediation is either not possible or will not be undertaken due to Business requirements, this must be clearly articulated with full justification provided. Reference to attached documents is acceptable.
5001 | Stop / Deallocate provisioned AWS resources | Cloudreach Migration Team |  |  | Not Required | Not Required | Not Required
5002 | Roll back DNS Changes | Sapphire Infrastructure Team |  |  | Not Required | Not Required | Not Required
5003 | Bring on-premises resources back | Sapphire Infrastructure Team |  |  | Not Required | Not Required | Not Required
5004 | Restart application services | Sapphire App Team |  |  | Not Required | Not Required | Not Required
5005 | Post-Rollback Application Testing | Sapphire App Team |  |  | Not Required | Not Required | Not Required
5006 | Client-Side Application Testing | Sapphire App Team |  |  | Not Required | Not Required | Not Required | 3rd Party and/or customer could be involved
END
6000 | Post Implementation activities
Activities to complete the Change that are outside the change window.
6001 | Initiate 5-day hypercare period | Cloudreach Migration Team |  |  | Not Started | Not Started | Not Started
6002 | Notify stakeholders of successful cutover (IT service desk & others) | Sapphire Programme Team |  |  | Not Started | Not Started | Not Started
6003 | Update Handover Documentation | Cloudreach Migration Team |  |  | Not Started | Not Started | Not Started
6004 | Handover to Ops Support | Cloudreach Migration Team |  |  | Not Started | Not Started | Not Started | Includes handover of relevant credentials, SSH keys, database passwords etc
END
7000 | Operations Onboarding
A list of activities for Operations to complete in regards to the support required for the application.
7001 | Handover Passport to Ops | Cloudreach Migration Team |  |  | Not Started | Not Started | Not Started
7002 | Validate resources against Application Passport | Sapphire Operations Team |  |  | Not Started | Not Started | Not Started
7003 | Check access to instance(s) | Sapphire Operations Team |  |  | Not Started | Not Started | Not Started
7004 | Raise onboarding issue to Sapphire Programme Team | Sapphire Operations Team |  |  | Not Started | Not Started | Not Started
7005 | Install required tools | Sapphire Operations Team |  |  | Not Started | Not Started | Not Started
7006 | Validate Backup Compliance | Sapphire Operations Team |  |  | Not Started | Not Started | Not Started
7007 | Internal Sign Off | Sapphire Operations Team |  |  | Not Started | Not Started | Not Started
7008 | Customer Sign Off - Go Live | Sapphire Programme Team |  |  | Not Started | Not Started | Not Started
7009 | Send comms to all stakeholders | Sapphire Programme Team |  |  | Not Started | Not Started | Not Started
END
8000 | Decommissioning
A list of activities to complete in regards to decomissioning the on-premises application infrastructure.
8001 | Raise request for decommissioning | Sapphire Programme Team |  |  | Not Started | Not Started | Not Started
END

## Infrastructure Manifest
Infrastructure Manifest
Read before you start: 1. Enter a new line item for each application virtual machine. 2. Select the Migration Strategy using the dropdown below 3. Complete all the columns for each virtual machine, there are dropdowns to select from for some columns. 4. For re-hosts, disks can be specified HOWEVER we can only resize disks and change layout POST migration. During the initial migration steps, they must be brought over with the same layout and disk size.
Migration Strategy |  | REHOST&RE-PLATFORM
Basic Info | [6 empty] | Compute |  |  |  | Networking | [6 empty] | Storage (Default GP3)
On-prem Name | Cloud Name | Role / Description | Migration Path | AWS Account | AWS Region | Domain-joined (Y/N) | OS (new if applicable) | EC2 Instance Type | vCPU | RAM (GB) | On-prem FQDN | Cloud FQDN (if applicable) | Target Subnet | On-prem Private IP | Cloud Private IP | On-prem Public IP | Cloud Public IP | /dev/sda1 | /dev/sdf | /dev/sdg | /dev/sdh | /dev/sdj | Comment
GEN2KTBRK01 | GEN2KTBRK01 | Remote Desktop Gateway / Broker - RDS Broker & Gateway | Rehost | DKIRK (708136847608) | London | Y |  | m5.large |  |  | KIRKBYTYRES.v2.sapphire |  | Application Subnet - A | 172.28.4.33
GEN2KTDC01 | DKIR01DCP01 | Domain Controller - Customer Active Directory | Replatform | DKIRK (708136847608) | London | Y | ami-062bc60a99aad8787 | t3.medium |  |  | KIRKBYTYRES.v2.sapphire |  | Data Subnet - A | 172.28.4.1 |  |  |  | 50GB
GEN2KTDC02 | DKIR01DCP02 | Domain Controller - Customer Active Directory | Replatform | DKIRK (708136847608) | London | Y | ami-062bc60a99aad8787 | t3.medium |  |  | KIRKBYTYRES.v2.sapphire |  | Data Subnet - B | 172.28.4.2 |  |  |  | 50GB
GEN2KTDMZ01 | GEN2KTDMZ01 | DMZ Server - DMZ Server | Rehost | DKIRK (708136847608) | London | Y |  | m5.large |  |  | KIRKBYTYRES.v2.sapphire |  | Application Subnet - A | 172.28.4.36
GEN2KTDMZUAT01 | - | DMZ Server - UAT Netalogue Web Server | Retire | [7 empty] | KIRKBYTYRES.v2.sapphire |  |  | 172.28.4.37
gen2kthana01pr | DKIR01HANAP01 | HANA - Hana Server Primary | Replatform | DKIRK (708136847608) | London | N | SUSE Linux Enterprise Server 12 SP5 | r5.8xlarge |  |  | KIRKBYTYRES.v2.sapphire |  | Data Subnet - A | 172.28.4.9 |  |  |  | 150GB | 500GB | 250GB | 250GB | 250GB | NOTE: All GP3 instances with 10k IOPS and throughput 500 for the HANA server
gen2kthana02dr | - | HANA DR - Hana Server Secondary | Retire | [7 empty] | KIRKBYTYRES.v2.sapphire |  |  | 172.28.4.10
gen2kthanauat01 | - | HANA - UAT HANA Server | Retire | [7 empty] | KIRKBYTYRES.v2.sapphire |  |  | 172.28.4.12
gen2kthb01 | - | HANA Heartbeat - Hana Heartbeat Server | Retire | [7 empty] | KIRKBYTYRES.v2.sapphire |  |  | 172.28.4.8
GEN2KTHM01 | GEN2KTHM01 | HANA Mgmt Server - Hana Management Server | Rehost | DKIRK (708136847608) | London | Y |  | r5.large |  |  | KIRKBYTYRES.v2.sapphire |  | Application Subnet - A | 172.28.4.7
GEN2KTHMUAT01 | - | HANA Mgmt Server - UAT Hana Management Server | Retire | [7 empty] | KIRKBYTYRES.v2.sapphire |  |  | 172.28.4.15
GEN2KTINT01 | GEN2KTINT01 | Integration Server - Intergration Server | Rehost | DKIRK (708136847608) | London | Y |  | m5.xlarge |  |  | KIRKBYTYRES.v2.sapphire |  | Application Subnet - A | 172.28.4.34
GEN2KTINT02 | GEN2KTINT02 | Integration Server - Intergration Server | Rehost | DKIRK (708136847608) | London | Y |  | m5.large |  |  | KIRKBYTYRES.v2.sapphire |  | Application Subnet - A | 172.28.4.35
GEN2KTINTUAT01 | - | Integration Server - UAT Warehouse Connect | Retire |  |  |  |  | m5a.large |  |  | KIRKBYTYRES.v2.sapphire |  |  | 172.28.4.38
GEN2KTINTUAT02 | - | Integration Server - UAT Bespoke Integration Server | Retire | [7 empty] | KIRKBYTYRES.v2.sapphire |  |  | 172.28.4.39
GEN2KTRDS01 | GEN2KTRDS01 | Remote Desktop Service - RDS Server | Rehost | DKIRK (708136847608) | London | Y |  | m5.xlarge |  |  | KIRKBYTYRES.v2.sapphire |  | Application Subnet - A | 172.28.4.3
GEN2KTRDS02 | GEN2KTRDS02 | Remote Desktop Service - RDS Server | Rehost | DKIRK (708136847608) | London | Y |  | m5.xlarge |  |  | KIRKBYTYRES.v2.sapphire |  | Application Subnet - A | 172.28.4.4
GEN2KTRDS03 | GEN2KTRDS03 | Remote Desktop Service - RDS Server | Rehost | DKIRK (708136847608) | London | Y |  | m5.large |  |  | KIRKBYTYRES.v2.sapphire |  | Application Subnet - A | 172.28.4.5
GEN2KTRDSUAT01 | - | Remote Desktop Service - UAT RDS Server | Retire | [7 empty] | KIRKBYTYRES.v2.sapphire |  |  | 172.28.4.13
GEN2KTSQL01 | GEN2KTSQL01 | SAP/SQL - Database Server | Rehost | DKIRK (708136847608) | London | Y |  | m5.2xlarge |  |  | KIRKBYTYRES.v2.sapphire |  | Data Subnet - A | 172.28.4.6
GEN2KTSQLUAT01 | - | SAP/SQL - UAT SQL Server | Retire | [7 empty] | KIRKBYTYRES.v2.sapphire |  |  | 172.28.4.14
UNIX Users & Groups
Name | Type (Local, AD) | Group/User |  | Description
Sudoers
Sudoers.d File | Instance

## AWS Security Group Rules
Platform Security Groups
Platform Security Groups are SGs that have been created for repeatable access requirements such as AD, DNS, HTTPS or SSH/RDP. Refer to the platform documentation or the AWS console to review the current rulesets for each security group.
Please confirm which platform SGs are required
Security Group |  | Purpose |  | Required
Remote / Console Access
Application Security Group(s)
Application Security Groups are SGs that will be created for this specific application and its requirements only.
Production
Inbound Ruleset
Priority | Name | Source | Destination | Ports / Protocol
Outbound Ruleset
Priority | Name | Source | Destination | Ports / Protocol
Non-Production
Inbound Ruleset
Priority | Name | Source | Destination | Ports / Protocol
Outbound Ruleset
Priority | Name | Source | Destination | Ports / Protocol

## Lists (hidden)
Lists
ID | Role
1 | Sapphire Project Manager
2 | Cloudreach Project Manager
3 | Customer Account Manager
4 | Sapphire Programme Team
5 | Sapphire App Team
6 | Sapphire Infrastructure Team
7 | Cloudreach Migration Team
8 | Sapphire Operations Team
9 | Customer
10 | 3rd Party
~END~
^

## Data Validation
AWS Accounts | AWS Subnets | AWS Regions | Migration Path
Management Account (593147995557) | Edge Subnet - A | London | Rehost
Master Sapphire Account (274894176448) | Edge Subnet - B | Frankfurt | Re-platform
Networking (435629205066) | Application Subnet - A | Ohio | Retire
Audit (770894895139) | Application Subnet - B | South Africa | Repurchase
Log Archive (856956497920) | Data Subnet - A |  | Re-factor
Sapphire-Sales | Data Subnet - B |  | Retain
DKIRK (708136847608)

## TimeZones (hidden)
Time zone
GMT Greenwich Mean Time Europe UTC
CET Central European Time Europe UTC + 1 hour
CST Central Standard Time Central America UTC - 6 hours
IST India Standard Time Asia UTC + 5:30 hours
BST British Summer Time Europe UTC + 1 hour
CEST Central European Summer Time Europe UTC + 2 hours
ADT Atlantic Daylight Time Atlantic UTC - 3 hours
ADT Atlantic Daylight Time North America UTC - 3 hours
AFT Afghanistan Time Asia UTC + 4:30 hours
AKDT Alaska Daylight Time North America UTC - 8 hours
AKST Alaska Standard Time North America UTC - 9 hours
ALMT Alma-Ata Time Asia UTC + 6 hours
AMST Armenia Summer Time Asia UTC + 5 hours
AMST Amazon Summer Time South America UTC - 3 hours
AMT Armenia Time Asia UTC + 4 hours
AMT Amazon Time South America UTC - 4 hours
ANAST Anadyr Summer Time Asia UTC + 12 hours
ANAT Anadyr Time Asia UTC + 12 hours
AQTT Aqtobe Time Asia UTC + 5 hours
ART Argentina Time South America UTC - 3 hours
AST Arabia Standard Time Asia UTC + 3 hours
AST Atlantic Standard Time Atlantic UTC - 4 hours
AST Atlantic Standard Time Caribbean UTC - 4 hours
AST Atlantic Standard Time North America UTC - 4 hours
AZOST Azores Summer Time Atlantic UTC
AZOT Azores Time Atlantic UTC - 1 hour
AZST Azerbaijan Summer Time Asia UTC + 5 hours
AZT Azerbaijan Time Asia UTC + 4 hours
B Bravo Time Zone Military UTC + 2 hours
BNT Brunei Darussalam Time Asia UTC + 8 hours
BOT Bolivia Time South America UTC - 4 hours
BRST Brasilia Summer Time South America UTC - 2 hours
BRT Brasília time South America UTC - 3 hours
BST Bangladesh Standard Time Asia UTC + 6 hours
BTT Bhutan Time Asia UTC + 6 hours
C Charlie Time Zone Military UTC + 3 hours
CAST Casey Time Antarctica UTC + 8 hours
CAT Central Africa Time Africa UTC + 2 hours
CCT Cocos Islands Time Indian Ocean UTC + 6:30 hours
CDT Central Daylight Time Australia UTC + 10:30 hours
CDT Cuba Daylight Time Caribbean UTC - 4 hours
CDT Central Daylight Time North America UTC - 5 hours
CET Central European Time Africa UTC + 1 hour
CKT Cook Island Time Pacific UTC - 10 hours
CLST Chile Summer Time South America UTC - 3 hours
CLT Chile Standard Time South America UTC - 4 hours
COT Colombia Time South America UTC - 5 hours
CST China Standard Time Asia UTC + 8 hours
CST Central Standard Time Australia UTC + 9:30 hours
CST Cuba Standard Time Caribbean UTC - 5 hours
CST Central Standard Time North America UTC - 6 hours
CVT Cape Verde Time Africa UTC - 1 hour
CXT Christmas Island Time Australia UTC + 7 hours
ChST Chamorro Standard Time Pacific UTC + 10 hours
D Delta Time Zone Military UTC + 4 hours
DAVT Davis Time Antarctica UTC + 7 hours
E Echo Time Zone Military UTC + 5 hours
EASST Easter Island Summer Time Pacific UTC - 5 hours
EAST Easter Island Standard Time Pacific UTC - 6 hours
EAT Eastern Africa Time Africa UTC + 3 hours
EAT East Africa Time Indian Ocean UTC + 3 hours
ECT Ecuador Time South America UTC - 5 hours
EDT Eastern Daylight Time Australia UTC + 11 hours
EDT Eastern Daylight Time Caribbean UTC - 4 hours
EDT Eastern Daylight Time North America UTC - 4 hours
EDT Eastern Daylight Time Pacific UTC + 11 hours
EEST Eastern European Summer Time Africa UTC + 3 hours
EEST Eastern European Summer Time Asia UTC + 3 hours
EEST Eastern European Summer Time Europe UTC + 3 hours
EET Eastern European Time Africa UTC + 2 hours
EET Eastern European Time Asia UTC + 2 hours
EET Eastern European Time Europe UTC + 2 hours
EGST Eastern Greenland Summer Time North America UTC
EGT East Greenland Time North America UTC - 1 hour
EST Eastern Standard Time Australia UTC + 10 hours
EST Eastern Standard Time Central America UTC - 5 hours
EST Eastern Standard Time Caribbean UTC - 5 hours
EST Eastern Standard Time North America UTC - 5 hours
ET Tiempo del Este Central America UTC - 5 hours
ET Tiempo del Este Caribbean UTC - 5 hours
ET Tiempo Del Este North America UTC - 5 hours
F Foxtrot Time Zone Military UTC + 6 hours
FJST Fiji Summer Time Pacific UTC + 13 hours
FJT Fiji Time Pacific UTC + 12 hours
FKST Falkland Islands Summer Time South America UTC - 3 hours
FKT Falkland Island Time South America UTC - 4 hours
FNT Fernando de Noronha Time South America UTC - 2 hours
G Golf Time Zone Military UTC + 7 hours
GALT Galapagos Time Pacific UTC - 6 hours
GAMT Gambier Time Pacific UTC - 9 hours
GET Georgia Standard Time Asia UTC + 4 hours
GFT French Guiana Time South America UTC - 3 hours
GILT Gilbert Island Time Pacific UTC + 12 hours
GMT Greenwich Mean Time Africa UTC
GST Gulf Standard Time Asia UTC + 4 hours
GYT Guyana Time South America UTC - 4 hours
H Hotel Time Zone Military UTC + 8 hours
HAA Heure Avancée de l'Atlantique Atlantic UTC - 3 hours
HAA Heure Avancée de l'Atlantique North America UTC - 3 hours
HAC Heure Avancée du Centre North America UTC - 5 hours
HADT Hawaii-Aleutian Daylight Time North America UTC - 9 hours
HAE Heure Avancée de l'Est Caribbean UTC - 4 hours
HAE Heure Avancée de l'Est North America UTC - 4 hours
HAP Heure Avancée du Pacifique North America UTC - 7 hours
HAR Heure Avancée des Rocheuses North America UTC - 6 hours
HAST Hawaii-Aleutian Standard Time North America UTC - 10 hours
HAT Heure Avancée de Terre-Neuve North America UTC - 2:30 hours
HAY Heure Avancée du Yukon North America UTC - 8 hours
HKT Hong Kong Time Asia UTC + 8 hours
HLV Hora Legal de Venezuela South America UTC - 4:30 hours
HNA Heure Normale de l'Atlantique Atlantic UTC - 4 hours
HNA Heure Normale de l'Atlantique Caribbean UTC - 4 hours
HNA Heure Normale de l'Atlantique North America UTC - 4 hours
HNC Heure Normale du Centre Central America UTC - 6 hours
HNC Heure Normale du Centre North America UTC - 6 hours
HNE Heure Normale de l'Est Central America UTC - 5 hours
HNE Heure Normale de l'Est Caribbean UTC - 5 hours
HNE Heure Normale de l'Est North America UTC - 5 hours
HNP Heure Normale du Pacifique North America UTC - 8 hours
HNR Heure Normale des Rocheuses North America UTC - 7 hours
HNT Heure Normale de Terre-Neuve North America UTC - 3:30 hours
HNY Heure Normale du Yukon North America UTC - 9 hours
HOVT Hovd Time Asia UTC + 7 hours
I India Time Zone Military UTC + 9 hours
ICT Indochina Time Asia UTC + 7 hours
IDT Israel Daylight Time Asia UTC + 3 hours
IOT Indian Chagos Time Indian Ocean UTC + 6 hours
IRDT Iran Daylight Time Asia UTC + 4:30 hours
IRKST Irkutsk Summer Time Asia UTC + 9 hours
IRKT Irkutsk Time Asia UTC + 8 hours
IRST Iran Standard Time Asia UTC + 3:30 hours
IST Israel Standard Time Asia UTC + 2 hours
IST Irish Standard Time Europe UTC + 1 hour
JST Japan Standard Time Asia UTC + 9 hours
K Kilo Time Zone Military UTC + 10 hours
KGT Kyrgyzstan Time Asia UTC + 6 hours
KRAST Krasnoyarsk Summer Time Asia UTC + 8 hours
KRAT Krasnoyarsk Time Asia UTC + 7 hours
KST Korea Standard Time Asia UTC + 9 hours
KUYT Kuybyshev Time Europe UTC + 4 hours
L Lima Time Zone Military UTC + 11 hours
LHDT Lord Howe Daylight Time Australia UTC + 11 hours
LHST Lord Howe Standard Time Australia UTC + 10:30 hours
LINT Line Islands Time Pacific UTC + 14 hours
M Mike Time Zone Military UTC + 12 hours
MAGST Magadan Summer Time Asia UTC + 12 hours
MAGT Magadan Time Asia UTC + 11 hours
MART Marquesas Time Pacific UTC - 9:30 hours
MAWT Mawson Time Antarctica UTC + 5 hours
MDT Mountain Daylight Time North America UTC - 6 hours
MHT Marshall Islands Time Pacific UTC + 12 hours
MMT Myanmar Time Asia UTC + 6:30 hours
MSD Moscow Daylight Time Europe UTC + 4 hours
MSK Moscow Standard Time Europe UTC + 3 hours
MST Mountain Standard Time North America UTC - 7 hours
MUT Mauritius Time Africa UTC + 4 hours
MVT Maldives Time Asia UTC + 5 hours
MYT Malaysia Time Asia UTC + 8 hours
N November Time Zone Military UTC - 1 hour
NCT New Caledonia Time Pacific UTC + 11 hours
NDT Newfoundland Daylight Time North America UTC - 2:30 hours
NFT Norfolk Time Australia UTC + 11:30 hours
NOVST Novosibirsk Summer Time Asia UTC + 7 hours
NOVT Novosibirsk Time Asia UTC + 6 hours
NPT Nepal Time Asia UTC + 5:45 hours
NST Newfoundland Standard Time North America UTC - 3:30 hours
NUT Niue Time Pacific UTC - 11 hours
NZDT New Zealand Daylight Time Antarctica UTC + 13 hours
NZDT New Zealand Daylight Time Pacific UTC + 13 hours
NZST New Zealand Standard Time Antarctica UTC + 12 hours
NZST New Zealand Standard Time Pacific UTC + 12 hours
O Oscar Time Zone Military UTC - 2 hours
OMSST Omsk Summer Time Asia UTC + 7 hours
OMST Omsk Standard Time Asia UTC + 6 hours
P Papa Time Zone Military UTC - 3 hours
PDT Pacific Daylight Time North America UTC - 7 hours
PET Peru Time South America UTC - 5 hours
PETST Kamchatka Summer Time Asia UTC + 12 hours
PETT Kamchatka Time Asia UTC + 12 hours
PGT Papua New Guinea Time Pacific UTC + 10 hours
PHOT Phoenix Island Time Pacific UTC + 13 hours
PHT Philippine Time Asia UTC + 8 hours
PKT Pakistan Standard Time Asia UTC + 5 hours
PMDT Pierre & Miquelon Daylight Time North America UTC - 2 hours
PMST Pierre & Miquelon Standard Time North America UTC - 3 hours
PONT Pohnpei Standard Time Pacific UTC + 11 hours
PST Pacific Standard Time North America UTC - 8 hours
PST Pitcairn Standard Time Pacific UTC - 8 hours
PT Tiempo del Pacífico North America UTC - 8 hours
PWT Palau Time Pacific UTC + 9 hours
PYST Paraguay Summer Time South America UTC - 3 hours
PYT Paraguay Time South America UTC - 4 hours
Q Quebec Time Zone Military UTC - 4 hours
R Romeo Time Zone Military UTC - 5 hours
RET Reunion Time Africa UTC + 4 hours
S Sierra Time Zone Military UTC - 6 hours
SAMT Samara Time Europe UTC + 4 hours
SAST South Africa Standard Time Africa UTC + 2 hours
SBT Solomon IslandsTime Pacific UTC + 11 hours
SCT Seychelles Time Africa UTC + 4 hours
SGT Singapore Time Asia UTC + 8 hours
SRT Suriname Time South America UTC - 3 hours
SST Samoa Standard Time Pacific UTC - 11 hours
T Tango Time Zone Military UTC - 7 hours
TAHT Tahiti Time Pacific UTC - 10 hours
TFT French Southern and Antarctic Time Indian Ocean UTC + 5 hours
TJT Tajikistan Time Asia UTC + 5 hours
TKT Tokelau Time Pacific UTC - 10 hours
TLT East Timor Time Asia UTC + 9 hours
TMT Turkmenistan Time Asia UTC + 5 hours
TVT Tuvalu Time Pacific UTC + 12 hours
U Uniform Time Zone Military UTC - 8 hours
ULAT Ulaanbaatar Time Asia UTC + 8 hours
UYST Uruguay Summer Time South America UTC - 2 hours
UYT Uruguay Time South America UTC - 3 hours
UZT Uzbekistan Time Asia UTC + 5 hours
V Victor Time Zone Military UTC - 9 hours
VET Venezuelan Standard Time South America UTC - 4:30 hours
VLAST Vladivostok Summer Time Asia UTC + 11 hours
VLAT Vladivostok Time Asia UTC + 10 hours
VUT Vanuatu Time Pacific UTC + 11 hours
W Whiskey Time Zone Military UTC - 10 hours
WAST West Africa Summer Time Africa UTC + 2 hours
WAT West Africa Time Africa UTC + 1 hour
WDT Western Daylight Time Australia UTC + 9 hours
WEST Western European Summer Time Africa UTC + 1 hour
WEST Western European Summer Time Europe UTC + 1 hour
WET Western European Time Africa UTC
WET Western European Time Europe UTC
WFT Wallis and Futuna Time Pacific UTC + 12 hours
WGST Western Greenland Summer Time North America UTC - 2 hours
WGT West Greenland Time North America UTC - 3 hours
WIB Western Indonesian Time Asia UTC + 7 hours
WIT Eastern Indonesian Time Asia UTC + 9 hours
WITA Central Indonesian Time Asia UTC + 8 hours
WST Western Sahara Summer Time Africa UTC + 1 hour
WST Western Standard Time Australia UTC + 8 hours
WST West Samoa Time Pacific UTC - 11 hours
WT Western Sahara Standard Time Africa UTC
X X-ray Time Zone Military UTC - 11 hours
Y Yankee Time Zone Military UTC - 12 hours
YAKST Yakutsk Summer Time Asia UTC + 10 hours
YAKT Yakutsk Time Asia UTC + 9 hours
YAPT Yap Time Pacific UTC + 10 hours
YEKST Yekaterinburg Summer Time Asia UTC + 6 hours
YEKT Yekaterinburg Time Asia UTC + 5 hours